## Sheet1 (2)
Next Steps | Priority | Notes | △
For find detail screens: only show the header and detail on the page (remaining list in the background is confusing). Then turn the headers (e.g. 'Tango Dances:') into 'Go back to list' | 01 - high
change alert on homepage to talk about scrolling down to see steps | 02 - high |  | new issue discovered after last usability test
Change 'how to' screen to 2 steps (watch and listen) with larger font and fewer words OR just make the homepage popup show 3 items: Scroll Down/Watch/Listen/HowTo/Scroll Down. Or just say there will be a video to show the user how it works | 03 - medium |  | How to screen: user was overwhelmed and clicked off of it as soon as they saw it saying that there was too much to read and the font was too small (potential solution: decrease words, increase fonts. Maybe just make it two steps: watch and listen)
Add screenshots to How To or say that there will be a video to show the user how it works | 03 - medium | easy | How to screen: the screenshots were absent - just placeholders
make the status bar not-opaque by making the background clear or not opaque | 04 - medium
Change up the order? Maybe put steps before dances? | 05 - medium
Annotations only: On the practice and video screens, have the dances play through in the order 1-6. If they start on 3, then 4-5-6-1-2. That is the default. Unless they press the repeat button. | 06 - low |  | Once the user plays one song, it stops and they can only replay that one song. (potential solution....Annotations only: On the practice screen, have the dances play through in the order 1-6. If they start on 3, then 4-5-6-1-2. That is the default. Unless they press the repeat button.)
Add a back button | 07 - low |  | When user selects a wrong item or changes their mind, they have to go through multiple screens to get back to the choices (potential solution: Add a 'back' button)
Buttons were too close together (potential solution: spread your buttons out a bit to make sure they can't click on two at the same time) | 11 - completed before last usability test |  | Buttons were too close together (potential solution: spread your buttons out a bit to make sure they can't click on two at the same time)
Can't read the text on the buttons. (potential solution: Enlarge text on buttons (1-2 pts max)) | 11 - completed before last usability test |  | Can't read the text on the buttons. (potential solution: Enlarge text on buttons (1-2 pts max))
Drop shadows look off - iOS is flatter. And it's confusing that they are different sizes. (potential solution: Make buttons look more like buttons/links. And make them all the same size. Use iOS template to make sure that all buttons are native UI.) | 11 - completed before last usability test |  | Drop shadows look off - iOS is flatter. And it's confusing that they are different sizes. (potential solution: Make buttons look more like buttons/links. And make them all the same size. Use iOS template to make sure that all buttons are native UI.)
Having logo on all screens is redundant and takes up space. (potential solution: Replace logo on all screens except the first.) | 11 - completed before last usability test |  | Having logo on all screens is redundant and takes up space. (potential solution: Replace logo on all screens except the first.)
Homepage (with instructions) is to busy and the text is too small. It's hard to follow. (potential solution: Enlarge text on homescreen and adjust layout so that only one idea is presented at a time (undo split screen layouts). This will make the homescreen longer.) | 11 - completed before last usability test |  | Homepage (with instructions) is to busy and the text is too small. It's hard to follow. (potential solution: Enlarge text on homescreen and adjust layout so that only one idea is presented at a time (undo split screen layouts). This will make the homescreen longer.)
Homescreen is overcrowded. (potential solution: Change homescreen from an instruction page. Add onboarding patterns that they only view once. Give them a link to re-access it if they need it. Maybe this is 5th menu item (? Button) that says "How to"???. On a website, there might be a 'How it works' menu on the right side (out of the way of the primary content) | 11 - completed before last usability test |  | Homescreen is overcrowded. (potential solution: Change homescreen from an instruction page. Add onboarding patterns that they only view once. Give them a link to re-access it if they need it. Maybe this is 5th menu item (? Button) that says "How to"???. On a website, there might be a 'How it works' menu on the right side (out of the way of the primary content)
Instructions on home page have weird text errors - wrapping. (potential solution: correct text wrapping on homescreen - e.g. Step 1) | 11 - completed before last usability test |  | Instructions on home page have weird text errors - wrapping. (potential solution: correct text wrapping on homescreen - e.g. Step 1)
Logo' looks funny. User suggested putting a product name even if it was a fake name. (potential solution: Replace 'Logo' with real name) | 11 - completed before last usability test |  | Logo' looks funny. User suggested putting a product name even if it was a fake name. (potential solution: Replace 'Logo' with real name)
On video screens, there's a lot of empty space that could better used because where the space is being used the text is too small. (potential solution: Make buttons move left to right instead of vertically. Alternative: make the links appear from a pull-down menu) | 11 - completed before last usability test |  | On video screens, there's a lot of empty space that could better used because where the space is being used the text is too small. (potential solution: Make buttons move left to right instead of vertically. Alternative: make the links appear from a pull-down menu)
Practice screen: add a repeat button that allows them to play the song over and over | 11 - completed before last usability test |  | Practice screen: add a repeat button that allows them to play the song over and over
Practice Screen: music player looks like it doesn't belong there (even though it's the main function of that page). The other elements on the screen get the users attention. (potential solution; remove scroll down portion with links to other videos. Figure out another way to link to them. Add swipe or button on the Practice screen so that contextual links can be brought up when user pushes a button - video of dance #1 + links to videos that teach 8 count basic and back ocho.) | 11 - completed before last usability test |  | Practice Screen: music player looks like it doesn't belong there (even though it's the main function of that page). The other elements on the screen get the users attention. (potential solution; remove scroll down portion with links to other videos. Figure out another way to link to them. Add swipe or button on the Practice screen so that contextual links can be brought up when user pushes a button - video of dance #1 + links to videos that teach 8 count basic and back ocho.)
The menu disappears on some screens. The user didn't know to scroll down. (potential solution: Make the menu a fixed item so it floats at the bottom) | 11 - completed before last usability test | need to add to annotations | The menu disappears on some screens. The user didn't know to scroll down. (potential solution: Make the menu a fixed item so it floats at the bottom)
The popup didn't go away when the user clicked it. (potential solution: Add screen without the popup.) | 11 - completed before last usability test |  | The popup didn't go away when the user clicked it. (potential solution: Add screen without the popup.)
The tables of dances and steps is too hard to read on a phone. (potential solution: On the screens that show the table of the database…for an iphone, you should prob only show 1-2 columns at a time. 3 is too much. You could hide the add'l info in a 'carousel' that swings to the right - swipe left and right to see it all. Or you could have it appear in a box when they click a 'see detail' link.) | 11 - completed before last usability test |  | The tables of dances and steps is too hard to read on a phone. (potential solution: On the screens that show the table of the database…for an iphone, you should prob only show 1-2 columns at a time. 3 is too much. You could hide the add'l info in a 'carousel' that swings to the right - swipe left and right to see it all. Or you could have it appear in a box when they click a 'see detail' link.)
User hit the play video button, but it wasn't obvious that the video was playing and it wasn't big enough for them to watch (potential solution: Add screen for viewing video in full screen for both dances and steps0 | 11 - completed before last usability test |  | User hit the play video button, but it wasn't obvious that the video was playing and it wasn't big enough for them to watch (potential solution: Add screen for viewing video in full screen for both dances and steps0
InVision: for screens where the pulldown menu is open, freeze it so that is at the top of the screen (may need to freeze from bottom) | 12 - completed after last usability test
Change all learn and practice to watch and listen. | 12 - completed after last usability test |  | Learn' and 'Practice' aren't clearly differentiated for the user. They used both when trying to watch and listen to music. (Potential suggestion: just use watch and listen throughout)
Change all learn and practice to watch and listen. | 12 - completed after last usability test | easy | Navigation on 'Learn' pages doesn't match the 'Learn' menu or the instructions on home page. (potential solution: change navigation on 'Learn' screens from 'view' to 'watch' to match instructions or make them all the same)
Remove all links from the first layer, just show the names of dances/steps, show the links and detail below them once they click on them | 12 - completed after last usability test |  | Too many places to click on for one dance or one step - two on the left, one on the right. (potential solution: remove all links from the first layer, just show the names of dances/steps, show the links and detail below them once they click on them)
Remove all links from the first layer, just show the names of dances/steps, show the links and detail below them once they click on them | 12 - completed after last usability test |  | Triple dots isn't intuitive. Only clicked on it as a last resort. (potential solution: put all links and detail in a layer below the names of each dance and step so that they have to click on the name (intuitive anyway) and then they have all related info and links in one place.
Remove all links from the first layer, just show the names of dances/steps, show the links and detail below them once they click on them | 12 - completed after last usability test | use the last option | User said they were confused by the multiple groups of navigation on the home page (potential solution: take the menu off the homepage or make homepage just visual and allow user to navigate with the one menu that is at the bottom of all pages. OR put the library on the home page and eliminate the 'select' flow.)
shorten status bar to prevent wrapping in InVision | 12 - completed after last usability test |  | new issue discovered after last usability test
Add color and pics to app | 12 - completed after last usability test |  | app looks boring. (potential solution: Add color based on apple guidelines - see screenshot. If using pastels, use only a set of coordinating pastels.)
Add color and pics to app | 12 - completed after last usability test |  | not aesthetically pleasing (potential solution: add color/pics)
change home icon to library/find | 12 - completed after last usability test |  | new issue discovered after last usability test
Adjust value on practice screen to reflect actual number of options | 12 - completed after last usability test | easy | on the Practice page, user hit the '2 more' button, but 7+ options appeared (potential solution: adjust the value to reflect the actual number of options)
Resize video screens | 12 - completed after last usability test | easy | part of video screens are cutoff on the phone (potential solution: resize)
Put the library on the homescreen and delete the 'select' flow | 12 - completed after last usability test | use the last option | It's not obvious from the home page that this app could do any of the tasks suggested (play music or watch videos). The user was looking for something that looked like music or video. (potential solutions: make the icons from home page more intuitive. OR make the 'How to' section a set of onboarding screens that they see when they first open the app. OR change the homescreen to show two major steps - listen and watch. OR just make the homescreen the library.
Put the library on the homescreen and delete the 'select' flow | 12 - completed after last usability test | use the first option | User went to 'Learn' and 'Practice' instinctively when directed to do a task. They used 'Select' as a last resort - even though that would have been the best route. (Potential solution: get rid of 'select' by making that the home page. Or change from 'select' to 'library' or 'browse'.)
Make all links the height of archive/more buttons (like email app) and make them take up the entire height (boxed-in) | 12 - completed after last usability test |  | Buttons were too small, hard for user to hit only one. (potential solution: make all buttons bigger like the size of of the archive/more buttons on an email when you slide left)
Center alerts | 12 - completed after last usability test | easy | user didn't notice the popups and thought the app wasn't working because they couldn't push other buttons. (potential solution: alerts need to be centered in the screen)
Assign a color to all buttons/links | 12 - completed after last usability test |  | User couldn't distinguish between buttons and non-buttons (potential solution: Designate one color for interactivity (e.g. buttons). Make sure that color doesn't compete with others.)
Assign a color to all buttons/links | 12 - completed after last usability test |  | User kept trying to click on the names of the dances and steps instead of using the buttons (Potential solutions: color code any buttons or words that are clickable; use the words of steps and dances as a clickable link that opens up the other options including video link, music link, and additional info)
Make menu items red (to show that they are clickable) | 12 - completed after last usability test |  | new issue discovered after last usability test

## old sheet
Source | Changes to make | Completed
Chris | take pics of the screenshots and put in onboarding
Chris | Replace all 'select' with Browse?
Chris | Having a 'back' button can be really helpful if they select the wrong item or change their minds
Chris | Annotations only: Make the menu a fixed item so it floats at the bottom
Chris | on the Practice page….value should be 7, not 2
Chris | Add screen for viewing video in full screen for both dances and steps | 2016-10-20
Chris | Change navigation on 'Learn' screens from 'view' to 'watch' | 2016-10-20
Chris | Correct text wrapping on homescreen (Step 1) | 2016-10-18
Chris | Practice Screen: remove scroll down. | 2016-10-18
Chris | Replace 'Logo' with real name | 2016-10-18
Chris | Add screen without the popup so it goes away when they click it. | 2016-10-18
Chris | Enlarge text on homescreen and adjust layout so that only one idea is presented at a time (undo split screen layouts). This will make the homescreen longer. | 2016-10-18
Chris | Make buttons look more like buttons/links. And make them all the same size (see home screen) | 2016-10-18
Chris | Enlarge text on buttons (1-2 pts max) | 2016-10-18
Chris | InVision only: Make the menu a fixed item so it floats at the bottom | 2016-10-18
for presentation | increase number of interviewees.
for presentation | Add persona? Probably not…only if you want to add a true beginner who is learning steps and a more advanced dancer who just wants to practice
iOS guidelines | Designate one color for interactivity (e.g. buttons). Make sure that color doesn't compete with others. If using pastels, use only a set of coordinating pastels.
iOS guidelines | Add color based on apple guidelines (see screenshot)
iOS guidelines | Replace logo on all screens (except 1) with color branding - iOS guidelines | 2016-10-20
Jason | spread your buttons out a bit to make sure they can't click on two at the same time
Jason | Invision and Annotations: ______
Jason | Annotations only: On the practice screen, have the dances play through in the order 1-6. If they start on 3, then 4-5-6-1-2. That is the default. Unless they press the repeat button.
Jason | Practice Screen: Add swipe or button on the Practice screen so that contextual links can be brought up when user pushes a button (video of dance #1 + links to videos that teach 8 count basic and back ocho) | 2016-10-21
Jason | On the screens that show the table of the database…for an iphone, you should prob only show 1-2 columns at a time. 3 is too much. You could hide the add'l info in a 'carousel' that swings to the right (swipe left and right to see it all). Or you could have it appear in a box when they click a 'see detail' link. | 2016-10-21
Jason | On video screens, use the space better - make buttons move left to right instead of vertically. (Alternative: make the links appear from a pull-down menu) | 2016-10-21
Jason | Use iOS template to make sure that all buttons are native UI (look like buttons and are differentiated from rest of text). Drop shadows look off - iOS is flatter. | 2016-10-20
Jason | Change homescreen from an instruction page. Add onboarding patterns that they only view once. Give them a link to re-access it if they need it. Maybe this is 5th menu item (? Button) that says "How to"???. On a website, there might be a 'How it works' menu on the right side (out of the way of the primary content) | 2016-10-20
Jason | Practice screen: add a repeat button that allows them to play the song over and over | 2016-10-20